## Checklist
Audit-Ready Supplier Compliance: 90-Day Plan
A 30/60/90-day implementation checklist for supplier evidence control
Status | Area | Check | Owner | Evidence / link | Notes
Not started | Days 1-30: define | Name the program owner and supporting roles
Not started | Days 1-30: define | Define the supplier record, evidence taxonomy, statuses, and approval rules
Not started | Days 1-30: define | Segment suppliers by risk and identify required documents
Not started | Days 1-30: define | Baseline missing, expired, and unreviewed evidence
Not started | Days 1-30: define | Define escalation and exception ownership
Not started | Days 31-60: centralize | Create one controlled record per supplier and site
Not started | Days 31-60: centralize | Link contacts, requirements, documents, specifications, and approval history
Not started | Days 31-60: centralize | Capture issue, expiry, review, and next-action dates
Not started | Days 31-60: centralize | Clean duplicate and obsolete records
Not started | Days 31-60: centralize | Pilot renewal and supplier follow-up workflows
Not started | Days 61-90: operationalize | Launch dashboards for missing, expiring, overdue, and pending evidence
Not started | Days 61-90: operationalize | Document reviewer decisions and exception resolution
Not started | Days 61-90: operationalize | Test retrieval against common auditor and customer questions
Not started | Days 61-90: operationalize | Set management metrics and review cadence
Not started | Days 61-90: operationalize | Assign open gaps and close the highest-risk items